**FAO/IPPC Technical Working Group on Quarantine and Phytosanitary Measures**

**Responsibilities for the development of training materials related to “Prevention, preparedness and response guidelines for *Spodoptera fruigiperda*”**

Primary target audience:

* NPPO Heads
* Pest risk analysis and legislation officers
* Inspection officers (heads and field officers)
* Diagnostic officers (heads and field officers)
* Surveillance officers (heads and field operators)
* Field operations officers

Secondary target audience:

* Producers
* Importers and exporters
* Academia

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| About | Activities | Target audience | Leads  | IPPC Secretariat staff | Existing training materials |
|  | **1. Background information on the pest** |
| 1. Background information on the pest |  A PPT or video to be elaborated on the basis of existing documents and to be used in various training sessions as a basis.  (February 2021) | All | Tek TAY *Supported by*XXX | Arop DENG |  |
|  | **2. General information on the biology of the pest** |
| 2. General information on the biology of the pest |  A PPT or video to be elaborated on the basis of existing documents and to be used in various training sessions as a basis.  (February 2021) | All | Tek TAY *Supported by* | Arop DENG |  |
|  | **3. Prevention and preparedness plan: when the pest is still absent** |
| 3.1 Pest Risk Analysis | A PPT on PRAs A PPT on legislation A PPT on inspection A didactic video on the inspection of some commodities **Webinar 2G** on PRA, legislation and inspection with the three regions (April 2021)**Webinar 2G** on PRA, legislation and inspection with the three regions  (April 2021)**WebinarR2N** on PRA, legislation and inspection with the three regions  (April 2021) | Pest risk analysis and legislation officers Inspection officers (heads)  | Mekki CHOUIBANI *Supported by* | Sarah BRUNEL |  |
| 3.2 Phytosanitary legislation | **Webinar 2** |  | Mekki CHOUIBANI *Supported by* | Sarah BRUNEL |  |
| 3.3 Inspection and diagnostics | **Webinar 2** for inspectionPPT and videos on the various diagnostic methods  **Webinar 3G** on diagnostic with the three regions (March 2021) **Webinar 3R** on diagnostic at the regional level (April 2021) **Webinar 3N** on diagnostic at the national level (April 2021) | Head Diagnostic officers in the 21 countries for the global webinar.Main diagnostic officers for the regional webinars.All diagnosticians for the national webinars. | Valerio LUCCHESI *Supported by* |  |  |
| 3.4 Surveillance plan | PPT and videos on surveillance methods  **Webinar 4G** on surveillance with the three regions (March 2021) **Webinar 4R** on surveillance at the regional level (April/March 2021)  **Webinar 4N** on surveillance at the national level (April/March 2021)  | NPPO Heads Surveillance officers (heads) for the Global webinarMain surveillance officers for the regional webinars.All surveillance officers for the national webinars. | Chris DALE *Supported by* | Qingpo YANG |  |
| 3.5 Communications and information sharing with various stakeholders | **Webinar 1** |  | Allison WATSONRoger DAY *Supported by* | Sara GIULIANI |  |
|  | **4. Response plan: when the pest is officially detected and confirmed** |
| 4.1 Delimiting surveys | **Webinar 6** on the implementation of contingency plans with the three regions (April 2021) **Webinar 6** on the implementation of contingency plans at the regional level (May 2021)**Webinar 6** on the implementation of contingency plans at the national level (May 2021) | Primary target audience in the 21 regions Primary target audience in the 21 regions All at the national level  | MariangelaCIAMPITTI *Supported by* |  |  |
| 4.2 Phytosanitary measures are to be implemented once an outbreak is officially found | **Webinar 6**Possible simulations of an outbreak with the support of OIRSA(June 2021) |  | MariangelaCIAMPITTI *Supported by* | Artur SHAMILOV |  |
| 4.3 Suppression of the pest to reduce pest populations | **Webinar 6** |  | Roger DAY *Supported by* |  |  |
| 4.4 Communication and information sharing  | **Webinar 6** |  | Allison WATSONRoger DAY *Supported by* | Sara GIULIANI |  |
|  | **Appendix** |
| FAW preparedness and contingency plans | A general PPT from the guidelines.  1-2 case study videos from two regions having such programme in place (Pacific and Europe).  **Webinar 1G** on SOPs for contingency plans with the three regions presenting these facts and allowing discussion with RPPOs and Heads of NPPOs (February 2021). A survey/forum/dialogue to collect the advances on setting *SOPs on how to draft preparedness and contingency plans* from the 21 countries with facilitation from the RPPOs. Nomination of staff within countries for each target audience (i.e. contact of the person in charge of surveillance, etc.). **Webinar 1R** on SOPs for contingency plans at the regional level (February 2021).**Webinar 1N** on SOPs for contingency plans at the national level (March 2021). PPT on the implementation of contingency plans | NPPO Heads Field programme Officers at the Global level – All primary target audience at the Regional levelAll NPPO staff within a country | Mariangela CIAMPITTI *Supported by* | Qingpo YANG |  |