**Action points from the 2022-11 TPDP meeting**

**TPDP - ACTION POINTS ARISING FROM NOVEMBER 2022 MEETING**

(by deadline)

|  | **Action** | **Agenda Item** | | **Responsible** | **Deadline** |
| --- | --- | --- | --- | --- | --- |
|  | Rationale to be transmitted to the secretariat:  - Begomovirus transmitted by *Bemisia tabaci* (2006-023): removal from TPDP work programme | 7.8 | Discipline lead and DP drafting group | | **15 November 2022** |
|  | Rationale to be transmitted to the secretariat:  - Citrus leprosis virus (2018-025): scope adjustment | 7.8 | Discipline lead and DP drafting group | | **30 November 2022** |
|  | * Draft DPs to be transmitted to the secretariat:   - Pospiviroid species (except Potato spindle tuber viroid (DP7))(2018-031): to open expert consultation  - Revision of DP 09 Genus *Anastrepha*  (2021-002): to open expert consultation  - Revision of DP 25 *Xylella fastidiosa*  (2021-003): to open expert consultation  *- Cronartium comandrae* Peck (2018-015): first draft  *- Bactrocera zonata* (Saunders, 1842)(2021-013): first draft  *- Heterobasidion annosum* (2021-015): first draft | 7.8 | Discipline leads and DP drafting groups | | **15 December 2022**: |
|  | Rationales to be submitted to the SC for e-decision:  - Tephritidae: Identification of immature stages of fruit flies of economic importance by molecular techniques (2006-028): scope adjustment  *- Puccinia graminis* f. sp. tritici UG 99  (2019-004): removal from the TPDP work programme | 7.8 | Discipline leads and DP drafting groups | | **31** **December 2022**  (tentatively) |
|  | * Draft DPs to be transmitted to the secretariat:   - Revision of DP 27 I*ps* spp. (2021-004): to be submitted to the SC for first consultation  *- Drosophila suzukii* (Diptera: Drosophilidae) (2021-017): first draft   * - Tomato brown rugose fruit virus (2021-025): first draft | 7.8 | Discipline leads and DP drafting groups | | **30 January 2023** |
| 1. . | Draft DPs to be transmitted to the secretariat:  - Revision of DP 27 I*ps* spp. (2021-004): to be submitted to the SC for first consultation  *- Drosophila suzukii* (Diptera: Drosophilidae) (2021-017): first draft  - Tomato brown rugose fruit virus (2021-025): first draft | 7.8 | Discipline leads and DP drafting groups | | **30 January 2023** |
|  | Rationale to be transmitted to the secretariat:  - Revision of DP 5 (*Phyllosticta citricarpa* (McAlpine)) Aa (2019-011): to be submitted to the SC recommending to be put in “pending status” | 7.8 | Discipline lead and DP drafting group | | **15 February 2023** |
|  | Draft DPs to be transmitted to the secretariat to open the notification period (5 January – 15 February or 1 July to 15 August 2023) - for further adoption:  - Genus *Ceratitis* (2016-001)  - *Mononychelus tanajoa* (2018-006) | 7.8 | Discipline lead and DP drafting groups | | **1 March 2023** |
|  | Draft DP to be transmitted to the secretariat:  - *Meloidogyne mali* (2018-019): first draft | 7.8 | Discipline lead and DP drafting group | | **31 March 2023** |
|  | Update the Specification TP 1 to be submitted to the SC for approval | 7.8 | Secretariat | |  |
|  | Transmit the updated document on “Quality assurance issues associated with diagnostic protocols for regulated pests” to be presented during the next TPDP meeting | 7.4 | Norman BARR | |  |
|  | Update the document on the Instructions to authors of diagnostic protocols according to the TPDP suggestions | 7.5 | Secretariat | |  |
|  | Submit the paper on the procedures for DPs without drafting group to the SC | 7.7 | Secretariat | |  |