**TPDP virtual meeting June 2025**

**Work programme 2025-2026**

**Review of the status of draft Diagnostic Protocols (DPs)**

*(Updated: 2025-05-27)*

| **Topic N.** | **Current Title** | **Priority** | **Discipline Lead**  | **Referee** | **Status** | **Notes** |
| --- | --- | --- | --- | --- | --- | --- |
| 2006-028  | Tephritidae: Identification of immature stages of fruit flies of economic importance by molecular techniques  | 1 | Juliet GOLDSMITH  | Norman BARR  | Draft DP under development | Secretariat to share the documents on the scope with the TPDP -> see document 06\_TPDP\_Tel\_2024 (done)Presented to the 2024 TPDP meeting in Yokohama. Next steps: * Expert consultation
* “Country” consultation in July 2025
 |
| 2018-025  | Citrus leprosis virus  | 1 | Vessela MAVRODIEVA  | Andrew Appiah  | Draft DP under development | Next step: expert consultation* Draft DPs back to Secretariat: 01 February 2024
* Draft DPs for expert consultation: 05 February – 01 March 2024\* (\*one month of expert consultation)
* Draft DPs revision based on expert consultation: 04-18 March 2024
* Draft DPs to editor: 19 March – 02 April 2024
* Draft DPs revision based on editor’s final review: 03 April 19 April 2024
* TPDP revision and approval (e-decision or virtual meeting) – tight deadline: 30 April or 02 May 2024
* SC e-decision for approval for consultation period (final deadline): 01 June 2024
* First draft exists, but not yet ready, need to follow up with – not ready for EC
* For 2025 TPDP face to face meeting (1st draft ready, but some hiccups with some authors, and thus will hand pick an expert)
 |
| 2018-030  | Psyllid vectors of *Candidatus Liberibacter solanacearum*  | 1 | Norman BARR   | Juliet GOLDSMITH   | Draft DP under development  | Next step”: expert consultationFollow up with lead author (probably to consultation period in January 2025, to discuss in detail at the next face to face meeting)Deadline to drafting group: 1 June 2024Progressing well, not likely to be ready by beginning of august. First draft likely after F2F meeting.Progressing.  |
| 2019-003  | *Microcyclus ulei*  | 1 | Robert TAYLOR | Yazmin RIVERA  | Topic added to the List of topics (drafting group incomplete)  | Drafting group formed at the 2023 TPDP meetingNext step: follow up with the authors and draft the DPThe IPPC secretariat will follow up with the DP drafting group to inform about the situation. Target next F2F meeting 2025Robert Taylor:as interim primary contact point for this draft until new discipline lead  |
| 2019-010  | *Pyricularia oryzae* (syn. *Magnaporthe oryzae*) on Triticum spp.  | 1 | Geraldine  | Yazmin  RIVERA  | Draft DP under development  | Next step: draft the DP Follow up with lead author, there is no draft, drafting group unresponsive – consider finding a new lead author, but check with the current group first.Geraldine can suggest an expert if needed.There is a DP drafting group. It needs to follow up with the authors. The IPPC secretariat will follow up with the DP drafting group to inform about the situation. Target next F2F meeting 2025Geraldine – interim focal point Call for DP authors in November 2024 |
| 2019-011  | *Revision of DP 5 (Phyllosticta citricarpa (McAlpine)) Aa* | 1 | Yazmin RIVERA   | Robert TAYLOR   | Pending status  | Proposal for revision of DP 05: *Phyllosticta citricarpa* presented to the TPDP meeting in Yokohama.(see document 22\_TPDP\_2024\_Oct)SC May 2025 approved the termination of the pending status. |
| 2021-001  | *Revision of DP 03: Trogoderma granarium Everts* | 1 | Norman BARR  | Juliet GOLDSMITH   | Draft DP under development  | Next step: To expert consultationDraft is not ready for expert consultation, Norman will try to encourage the group. Norman indicated (via email) that the draft would be ready by Northen hemisphere summer of 2024 for ECNo draft yet – follow up, to try to get it by August |
| 2021-016  | *Spodoptera frugiperda (Fall Armyworm)* | 1 | Juliet GOLDSMITH  | Norman BARR  | Topic added to the List of topics  | Drafting group formed at the 2023 TPDP meetingNext step: follow up with the authors and draft the DP 🡪 done. DP drafting group contacted and committed.Draft promised by early august by authors. Lead author is not reachable. Secretariat to try to follow up with the lead author. Diego (Columbia).Follow-up done; author is online again.F2F meeting in 2025? |
| 2021-017  | *Drosophila suzukii (Diptera: Drosophilidae)* | 1 | Norman BARR  | Juliet GOLDSMITH  | Draft DP under development | Good draft, needs last reviewNext steps: To expert consultationNorman via email: draft to be sent to the secretariat end of July 2024Draft ready for EC. Currently in review by referee. To be sent to the secretariat end of July 2024Presented to the 2024 TPDP meeting in Yokohama. Expert consultation in May 2025. |
| 2021-025  | *Tomato brown rugose fruit virus* | 1 | Vessela MAVRODIEVA  | Géraldine ANTHOINE, Andrew APPIAH | Draft DP under development | Next steps: Follow up with the drafting group and produce a draft DPNo draft, Vessela to discuss the plan with DP drafting group: try to produce a draft by 1 JuneTentative for the 2025 TPDP face to face meeting |
| 2018-031 | Pospiviroid species (except Potato spindle tuber viroid (DP 7))  | 2 | Vessela MAVRODIEVA   | , Andrew APPIAH | Draft DP under development (consultation period Jan 2024) | Completed the consultation period in Jan 2024Next step: review of comments and revision of DP by the discipline lead TPDP to review the draft and responses to comments at the next F2F 2024 meetingPresented to the 2024 TPDP meeting in Yokohama. Next steps: * For DP notification period July 20205
 |
| 2018-032  | *Acidovorax avenae* subsp. *citrulli* | 2 | Robert TAYLOR   | Géraldine ANTHOINE   | Draft DP under development  | Draft in progress, not seen yet, third author disappeared. Kohei Osaki, Agriculture, Forestry and Fisheries Research Council, Japan has been accepted as another co-author for this protocol. The group is now working on a draft. Unlikely protocol will be ready for face to face meeting in Japan.Tentative for the 2025 TPDP face to face meeting |
| 2019-006  | *Amaranthus palmeri*  | 2 | Vijayasankar RAMAN | Juliet GOLDSMITH   | Draft DP under development  | No draft, Norman to follow up with ColetteNext steps: Follow up with the drafting group and produce a draft DPAuthors requested more time to perform diagnostic assessments before drafting methods. Protocol not ready for face to face in Japan.IPPC secretariat will follow up with the authors and inform about the new DL. |
| 2019-007  | *Solanum rostratum*  | 2 | Vijayasankar RAMAN | Géraldine ANTHOINE  | Draft DP under development  | No draft, Norman to reach outNext steps: Follow up with the drafting group and produce a draft DPAuthors generated a first outline for draft that requires additional information and then DL review before presenting to EC or TPDP. Protocol not ready for face to face in Japan.IPPC secretariat will follow up with the authors and inform about the new DL. |
| 2021-014  | *Dickeya spp. on Solanum tuberosum* | 2 | Robert TAYLOR  | Géraldine ANTHOINE  | Draft DP under development  | First draft, needs revision Next step: To expert consultationThere is an updated EPPO protocol, take into account the updated version – if neededHave received a draft. Needs to be edited into IPPC format but all the technical information is included. Could consider for expert consultation A draft could be presented at the face to face meeting.Presented to the 2024 TPDP meeting in Yokohama. Expert consultation in May 2025 |
| 2018-019  | *Meloidogyne mali*  | 3 | Géraldine ANTHOINE | Norman BARR  | Draft DP under development  | Approved for consultation (consultation period July 2024)Next step: After consultation* Draft DP and comments to DL by 1 October for revision based on consultation comments
* Draft DP and responses to comments sent to the Secretariat by 11 October 2024
* Tentative: TPDP review at the F2F meeting 21-26 October (Japan)

Presented to the 2024 TPDP meeting in Yokohama. Next steps: * DP Notification July 2025
 |
| 2018-015  | *Cronartium comandrae* Peck  | 4 | YazminRIVERA   | Géraldine ANTHOINE Julie  PATTEMORE   | Draft DP under development | First draft reviewed by referees; second draft need an extra expert.TPDP agreed with Yasmin to contact further authors if neededNext step: to finalize draft for expert consultation.Last update: DL consulted with the lead author for the and they have reached out to a few other North American SMEs without much success to review the DP, so they will proceed with what the two-author team has drafted if no responses are received one last time. Possibly ready by early summer to have it reviewed by the referee before entering the Expert Consultation. DL has the draft, but have not reviewed yet. Planning to review to submit by mid-August.Presented to the 2024 TPDP meeting in Yokohama. Next steps: * Expert consultation
 |
| 2023-009 | High-throughput sequencing identification of pure culture of phytopathogenic regulated bacteria isolated from plants | 2 | Ms. Yazmin Rivera RIVERA (US, 2023-10) | Mr. Robert TAYLOR (NZ, 2023-11) | Topic added to the List of topics | Already met with the Lead author.Under progress. |
| 2023-010 | *Alopecurus myosuroides* | 3 | Vijayasankar RAMAN (US, 2023-10) | Mme. Géraldine ANTHOINE (FR, 2023-10)Dr. Norman BARR (US, 2023-10) | Topic added to the List of topics | Authors to be selected at the TPDP meeting in Yokohama (see documents 23\_TPDP\_2024\_Oct and 24\_TPDP\_2024\_Oct)IPPC secretariat will follow up with the authors and inform about the new DL. |
| *2023-013* | *Bactrocera zonata and Bactrocera correcta* | 2 | Dr. Norman BARR (US, 2023-10)Ms. Juliet GOLDSMITH (SR, 2023-10) | Mme. Géraldine ANTHOINE (FR, 2023-10) | Topic added to the List of topics | Topic is being merged with *B. zonata*. A draft version is expected by August 30 for EC. Presented to the 2024 TPDP meeting in YokohamaExpert consultation in May 2025..  |
| *2023-016* | *Bactrocera tsuneonis and Bactrocera minax* | 2 | Dr. Norman BARR (US, 2023-10) | David Ouvrard | Topic added to the List of topics | Very early stage.  |
| *2023-026* | *Avocado sun blotch viroid* | 1 | Andrew APPIAH (GH, 2023-10) | Ms. Vessela Assenova MAVRODIEVA (US, 2023-10) | Topic added to the List of topics | Meeting has been held with the Lead author to develop timelines for drafting the DP.Draft DP being developed.  |
| *2023-029* | *Thaumatotibia leucotreta* | 1 | Ms. Juliet GOLDSMITH (SR, 2023-10) | Dr. Norman BARR (US, 2023-10)David Ouvrad | Topic added to the List of topics | Early stages |

**Recommendation**

The TPDP is invited to

1. *review* the entire workplan and ask the discipline leads for an update on each topic