# Action plan of information exchange DPRK

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No | Expected results(ER) | Action | Deadline | Responsibility | Stakeholder | Resulted materials |
| 1 | Development of contact method to internet and IPP/APPPC | Act1-1 MoA recognize importance of information exchange and admit to contact to internet and IPP | July,2011 | Senior officer, MoA | CPPS, Crop Production Department ,MoA | Agreement document |
| Act1-2 admit of FAO office in Pyongyang to contact internet and take all necessary proceedings | September, 2011 | Contact point, FAO office in Pyongyang | editor | Admitted documents |
| 2 | Contact with IPP/APPPC for information exchange | Act 2-1 Detailed information on phytosanitary measure collection from concerned agency and screened | August, 2011 | Editor | CPPS, AAS,MoA,  CPQS and other agencies | Collected data base |
| Act 2-2 Admit of necessary information admitted by concerned Agency | August, 2011 | Editor | MoA | Admitted Document |
| Act 2-3 Information upload to IPP/APPC | September(follow to Act 1-2) | Editor | FAO office, Pyongyang | Uploaded information |
| 3 | Development of phytosanitary site in internal website | Act 3-1 Admit of MoA to develop phytosanitary site in his internal website | July, 2011 | Senior officer, MoA | Editor, ,Computer center ,MoA | Admitted document |
| Act 3-2 Development of Phytosanitary site in internal website depending on understand of IPP | December, 2011 | Computer center, MoA | MoA, CPPS,AAS | Phytosanitary site in internal website |
| 4 | Training workshops on internal information exchange | Act 4-1 Curricular for internal information exchange for co-farms as well as higher management boards | December,2011 | Computer Center,MoA | CPPS, MoA, Farm management boards | Curricular |
| Act 4-2 Initial Training workshop to Province Farm Management Boards and Province Plant Protection Stations | January,2012 | Crop production department, MoA | Province Farm Management Boards, Province Plant Protection Station | Participant list |
| Act 4-3 Secondary training workshops to County Farm Management Boards and co farms | February,2012 | All Province farm management boards | County Farm Management Boards, County Plant Protection Station | Participant list |