WORK PROGRAMME TPFQ 2014-15

(last updated 20 September 2014)

2014-15 Task Descriptions for the TPFQ

| Task Description | Expected delivery date |
| --- | --- |
| ISPM 15 (2009) Explanatory Document | SC e-Decision 10 February 2014 |
| Heat Treatment (HT) for ISPM 15 (2009) Explanatory (Guidance) Document | SC e-Decision 10 February 2014 |
| Methyl Bromide (MB) for ISPM 15 (2009) Explanatory (Guidance) Document | SC e-Decision 10 February 2014 |
| Review forest seed annex to the Draft ISPM for the movement of seed for propagation. | Prior to SC Meeting Nov 2014 |
| ISPM 15 (2009) Treatment Criteria | Prior to SC Meeting May 2015 |
| Developing the “Cardiff Protocol” with IFQRG working group | Prior to SC Meeting May 2015 |
| High moisture content in wood and penetration of methyl bromide | Prior to SC Meeting Nov 2014 |
| Recommendation for an ISPM 15 Workshop on Implementation | Prior to SC Meeting Nov 2014 |
| Recommendation for a minor review of annex 1 of ISPM 15 | Prior to SC Meeting Nov 2014 |
| Manage IFQRG/IPPC Joint Work Programme | On-going |

2014-15 Work Programme for the TPFQ

| Date | TPFQ Action | Responsible Person(s) |
| --- | --- | --- |
| 2014 |  |  |
| 2014 July |  |  |
| 07/~06 | TPFQ July 2014 Virtual Meeting– Review CPM 9 and SC reports, prepare for IFQRG 12. | TPFQ |
| 2014 September |  |  |
| 09/08 – 09/12 | IFQRG 12 – Rome | TPFQ |
| 09/15 – 09/19 | Handicrafts EWG – Rome | Sela |
| 2014 October |  |  |
| 10/~06 | TPFQ October 2014 Virtual Meeting– Review IFQRG 12 report, prepare for November SC. | TPFQ |
| 2014 November |  |  |
| 11/10 – 11/14 | 2014 November Standards Committee Meeting | Aliaga/Forest/ Wlodarczyk |
| 2015 February |  |  |
| 02/~06 | TPFQ February 2015 Virtual Meeting – Set Calendar for 2015, finalise documents for May SC meeting. | TPFQ |
| 2015 March |  |  |
| 03/16 – 03/20 | (April) CPM 10 | Aliaga/Forest/ Wlodarczyk |
| 2015 May |  |  |
| 05/04 – 05/08 | May 2013 Standards Committee Meeting | Aliaga/Forest/ Wlodarczyk |
| 05/11 – 05/15 | 2013 Standards Committee 7 Meeting |  |
| 2015 July |  |  |
| First weeks | TPFQ July 2015 Virtual Meeting– Review CPM 9 and SC reports, prepare for IFQRG 13. | TPFQ |
| 2015 September |  |  |
| Tentative | IFQRG 13 – Manchester, England (Tentative) | TPFQ |
| 2015 October |  |  |
| First week | TPFQ October 2015 Virtual Meeting– Review IFQRG 13 report, prepare for November SC. | TPFQ |
| 2015 November |  |  |
| 11/16 – 11/20 | 2015 November Standards Committee Meeting | Aliaga/Forest/ Wlodarczyk |